Vehicle Parking System (VPS)
Product Backlog & Sprint Execution Plan

Part-1 Deliverable: Backlog Creation, Story Points & Two-Sprint Plan (ETA: 12-Oct-2026)

| Organization & Project: | ParkMatrix / Vehicle Parking System |
| --- | --- |
| Repository: | https://github.com/ParkMatrix/vehicle-parking-system |
| Technology Stack: | MERN Stack (MongoDB, Express.js, React, Node.js) |
| Date & Baseline: | 11-Oct-2026 / 12-Oct-2026 (Version 1.0) |
| Deliverable Scope: | Part-1: Project Backlog, Story Points, Team Assignment, 2 Sprints |
| Authors / Team 5: | Preksha C M (QA Lead), Nishant H (PO/Dev), Siddesh V S (Dev Lead), Salasha V (Security) |

# 1. Executive Summary & Deliverables Verification

This document details the complete Product Backlog and Agile Sprint Plan created for the Vehicle Parking System (Team 5). Every functional requirement (FR), non-functional requirement (NFR), and security requirement (SR) established in the SRS has been translated into an actionable GitHub Issue with full traceability to the Software Architecture Document (SAD) and Software Test Plan (STP).

| Part-1 Deliverable Item | Status | Implementation Evidence |
| --- | --- | --- |
| a. Create Project & link with repo | Configured | Repo ParkMatrix/vehicle-parking-system linked; Board structure defined. |
| b. Use FR & NFR to create backlogs in Git | COMPLETED | All 29 requirements converted to Issues #24 to #52 with User Stories & Acceptance Criteria. |
| c. Assign Story Points to each backlog item | COMPLETED | Fibonacci story points (1, 2, 3, 5, 8) assigned across all 29 issues with 'sp: X' labels. |
| d. Assign stories to team members | COMPLETED | 100% of issues assigned across 4 team members matching modular ownership. |
| e. Plan Two Sprints | COMPLETED | Sprint 1 (44 SP, 15 items) and Sprint 2 (44 SP, 14 items) planned with Milestones. |
| f. Sprint Dry Run (12-Oct to 16-Oct) | Scheduled | 1-week practice window for Git branching, PR reviews, CI/CD, and local setups. |
| g. Backlog Adjustment Window (until 19-Oct) | Scheduled | Final backlog refinement buffer prior to Sprint 1 development execution. |

# 2. Product Backlog (29 Baselined Requirements)

The Product Backlog encompasses 29 items (18 FRs, 6 NFRs, 5 SRs) totaling 88 Story Points, evenly distributed across two execution sprints.

| Issue | Req ID | Requirement Title | Category | Assignee | SP | Sprint | Test Ref |
| --- | --- | --- | --- | --- | --- | --- | --- |
| #24 | VPS-F-001 | User registration | Functional | Nishant-Hegde | 3 | Sprint 1 | TC-F-001 |
| #25 | VPS-F-002 | User login (JWT) | Functional | Nishant-Hegde | 3 | Sprint 1 | TC-F-002 |
| #26 | VPS-SR-004 | Secure password hashing (bcrypt) | Security | Nishant-Hegde | 2 | Sprint 1 | TC-S-004 |
| #27 | VPS-SR-001 | Authentication on protected APIs | Security | Preksha-a11y | 3 | Sprint 1 | TC-S-001 |
| #28 | VPS-F-003 | Register vehicle | Functional | Preksha-a11y | 3 | Sprint 1 | TC-F-003 |
| #29 | VPS-F-004 | View/update vehicle details | Functional | Preksha-a11y | 2 | Sprint 1 | TC-F-004 |
| #30 | VPS-SR-002 | Role-based access control (RBAC) | Security | Preksha-a11y | 3 | Sprint 1 | TC-S-002 |
| #31 | VPS-F-005 | Create parking slot | Functional | siddeshvs351 | 3 | Sprint 1 | TC-F-005 |
| #32 | VPS-F-006 | Update slot status | Functional | siddeshvs351 | 2 | Sprint 1 | TC-F-006 |
| #33 | VPS-F-007 | Slot status view (interactive grid) | Functional | siddeshvs351 | 5 | Sprint 1 | TC-F-007 |
| #34 | VPS-F-008 | Available-slot picker on entry | Functional | salashav | 3 | Sprint 1 | TC-F-008 |
| #35 | VPS-F-009 | Record vehicle entry (session) | Functional | salashav | 5 | Sprint 1 | TC-F-009 |
| #36 | VPS-F-010 | Mark slot occupied on entry | Functional | salashav | 2 | Sprint 1 | TC-F-010 |
| #38 | VPS-F-013 | Record vehicle exit | Functional | salashav | 3 | Sprint 1 | TC-F-013 |
| #39 | VPS-F-014 | Free slot on exit | Functional | salashav | 2 | Sprint 1 | TC-F-014 |
| #37 | VPS-F-018 | One active session per vehicle | Functional | salashav | 3 | Sprint 2 | TC-F-018 |
| #40 | VPS-NF-003 | RBAC verification tests | Non-Functional | Nishant-Hegde | 3 | Sprint 2 | TC-N-003 |
| #41 | VPS-NF-004 | Slot-session consistency check | Non-Functional | salashav | 3 | Sprint 2 | TC-N-004 |
| #42 | VPS-F-011 | Search active vehicle | Functional | siddeshvs351 | 3 | Sprint 2 | TC-F-011 |
| #43 | VPS-F-012 | Show current slot of parked vehicle | Functional | siddeshvs351 | 2 | Sprint 2 | TC-F-012 |
| #44 | VPS-NF-001 | Performance test (p95 < 2s) | Non-Functional | siddeshvs351 | 5 | Sprint 2 | TC-N-001 |
| #45 | VPS-NF-005 | Browser compatibility & error toasts | Non-Functional | Nishant-Hegde | 2 | Sprint 2 | TC-N-005 |
| #46 | VPS-F-015 | Parking history | Functional | Preksha-a11y | 3 | Sprint 2 | TC-F-015 |
| #47 | VPS-F-017 | Audit events for sensitive actions | Functional | Preksha-a11y | 5 | Sprint 2 | TC-F-017 |
| #48 | VPS-SR-005 | No secrets in audit log | Security | Preksha-a11y | 2 | Sprint 2 | TC-S-005 |
| #49 | VPS-NF-006 | Audit retention and retrieval | Non-Functional | Preksha-a11y | 3 | Sprint 2 | TC-N-006 |
| #50 | VPS-F-016 | Admin occupancy dashboard | Functional | Nishant-Hegde | 5 | Sprint 2 | TC-F-016 |
| #51 | VPS-NF-002 | Availability: health check & uptime | Non-Functional | Nishant-Hegde | 3 | Sprint 2 | TC-N-002 |
| #52 | VPS-SR-003 | HTTPS/TLS in production | Security | Nishant-Hegde | 2 | Sprint 2 | TC-S-003 |

# 3. Sprint 1 Plan (19-Oct to 23-Oct-2026)

Sprint Goal: Implement and deliver the functional core Minimum Viable Product (MVP). At the end of Sprint 1, an end-to-end user journey is fully operational: User Registration -> Login -> Slot Creation -> Slot Grid View -> Vehicle Entry -> Occupancy Update -> Vehicle Exit -> Slot Freeing.

Scope: 15 Backlog Items | 44 Story Points | Milestone: 'Sprint 1: Core MVP & Parking Operations (19 Oct - 23 Oct 2026)'

Nishant H (8 SP): User registration (#24), User login (#25), Password hashing (#26)

Preksha C M (11 SP): JWT protected APIs (#27), Vehicle registration (#28), Vehicle update (#29), RBAC middleware (#30)

Siddesh V S (10 SP): Slot creation (#31), Slot status updates (#32), Interactive Slot Grid view UI (#33)

Salasha V (15 SP): Available slot picker (#34), Record entry session (#35), Mark slot occupied (#36), Record exit session (#38), Free slot on exit (#39)

Sprint 1 Video Deliverable: A 1-minute video demonstration of the working MVP (registering user, viewing slots, parking car, freeing slot) will be recorded and committed to the repository by 23rd October 2026.

# 4. Sprint 2 Plan (26-Oct to 30-Oct-2026)

Sprint Goal: Complete all advanced features, security hardening, administrative dashboards, audit logging, and comprehensive Non-Functional Requirement (NFR) verification, culminating in the Final Project Freeze.

Scope: 14 Backlog Items | 44 Story Points | Milestone: 'Sprint 2: Tracking, Audit, NFRs & Hardening (26 Oct - 30 Oct 2026)'

Nishant H (15 SP): Admin occupancy dashboard (#50), Automated RBAC tests (#40), Browser compatibility (#45), Availability monitor (#51), HTTPS/TLS (#52)

Preksha C M (13 SP): Parking history (#46), Audit event logging (#47), Secret redaction (#48), Audit retention & retrieval (#49)

Siddesh V S (10 SP): Search active vehicle (#42), Show current slot (#43), Performance load testing p95 < 2s (#44)

Salasha V (6 SP): Single active session constraint (#37), Slot-session consistency validator (#41)

Sprint 2 Video Deliverable & Project Freeze: A comprehensive 2-minute video demonstrating the fully integrated system, audit logging, and metrics dashboard will be recorded and uploaded. All development will freeze on 30th October 2026.

# 5. Team Velocity & Capacity Distribution

| Team Member | Role | Sprint 1 SP | Sprint 2 SP | Total SP | Issues |
| --- | --- | --- | --- | --- | --- |
| Nishant H | Product Owner / Dev | 8 | 15 | 23 | 8 |
| Preksha C M | QA Lead / Tester | 11 | 13 | 24 | 8 |
| Siddesh V S | Dev Lead / Tester | 10 | 10 | 20 | 6 |
| Salasha V | Security Tester / Dev | 15 | 6 | 21 | 7 |
| Total / Velocity | Team 5 Capacity | 44 | 44 | 88 | 29 |